## Sprint
Tasks | Product Backlog Item(s) | Description | Team | Status | Comments | Original Estimate (Hours) | New Estimate (Hours) | Change | Revised Value (Hours) | Amount Remaining (Hours) | Start | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday
scene 4 resize rain particle image | 10 |  | Marco Brito | 3 - Completed | rain | 0.5 |  |  | 0.5 | 0 | [5 empty] | 0.5
scene 4 create asset for hand position | 10 |  | Marco Brito | 2 - In Progress | rain | 1 | [9 empty] | 0.5
scene 4 create cloud asset for people (Sprite Sheet) | 10 |  | Marco Brito | 1 - Not Started | rain | 1
scene 2: implement smoke assets with shader | 16 |  | Zara Tooth | 2 - In Progress | lights | 1 | 6 | 5 | 6 | 6 | 4
scene 2: particles connecting with active user hand locations if close enough | 16 |  | Zara Tooth | 3 - Completed | lights | 3 |  |  | 3 | 1 | 1 |  |  | 1 |  |  | 1
scene 2 implement hex particles color fading in when connected to hands | 20 |  | Zara Tooth | 3 - Completed | lights | 5 | 6 |  |  |  | 0.5 | 4 |  |  |  |  | 1.5 | 1.5
scene 2: implement hexparticles growing when connected to hands | 20 |  | Zara Tooth | 3 - Completed | lights | 3 | [10 empty] | 0.5 | 0.5
scene 2 hex particles get assigned a random color upon creation | 20 |  | Zara Tooth | 3 - Completed | lights | 1 | [11 empty] | 1
scene 2: particles attach to hand and get dragged by user | 20 |  |  | 1 - Not Started | lights | 4 |  |  | 4 | 4
scene 2 particles can be thrown by user/ get disconnected if delta v is too high | 20 |  |  | 1 - Not Started | lights
scene 2: particle/hand connections are dynamic and boucy | 20 |  |  | 1 - Not Started | lights
scene 3: generate semi random geometry for geo particles | 17 |  | Ryan Bottriell | 3 - Completed | geo | 3 | 5 | 2 | 5 | 2.5 |  |  |  | 2 |  |  | 0.5 | 2
scene 3: animate geometry over time | 17 |  | Ryan Bottriell | 3 - Completed | geo | 1 | [7 empty] | 0.5 |  |  |  | 0.5
scene 3 particle breaks apart after explosion | 21 |  |  | 1 - Not Started | geo
scene 3: create particle effect for particle explosion | 21 |  | Matthew Fournier | 2 - In Progress | geo | 3 | [6 empty] | 0.5 | 1.5
scene 4: create vector grid for rain movement | 18 |  |  | 1 - Not Started | rain | 3
scene 4 rain is influenced by vector grid | 18 |  |  | 1 - Not Started | rain
scene 4 create cloud particle for people particles | 18 |  |  | 1 - Not Started | rain
scene 4 rain management to allow clouds to create particles | 18 |  |  | 1 - Not Started | rain
scene 4 cloud particles create rain | 18 |  |  | 1 - Not Started | rain
[5 empty] | Original | 29.5 |  | 7 | 18.5 | 13.5
[5 empty] | Revised | 18.5 |  |  |  | Daily Effort |  | 4 | 0.5 | 5 | 0 | 1 | 3.5 | 5.5
[5 empty] | Additional | -11 |  |  |  | Effort to Date |  | 19.5 | 0.5 | 5.5 | 5.5 | 6.5 | 10 | 15.5
[5 empty] | % Increase | -37.29% |  |  |  | Effort Left |  | -1 | 18 | 13 | 13 | 12 | 8.5 | 3
[10 empty] | % Remaining | 100% | -3.39% | 61.02% | 44.07% | 44.07% | 40.68% | 28.81% | 10.17%
[5 empty] | Remaining | 13.5
[5 empty] | % Remaining | 72.97%
[5 empty] | Team Size | 4
[5 empty] | Days Effort (est. @80%) | 0.52734
Note on A1: Short name. Should be unique.
Note on B1: This is a reference to the ID defined in the Product Backlog, if applicable.
Note on C1: Longer description of the work item. If it references any external documents, they should be listed here.
Note on D1: Who on the team has taken ownership of this work item.
Note on E1: Current status of this task. This can be used to ensure multiple people do not work on the same task. The filter can also be used to filter out any tasks that have already been completed.
Note on F1: Any additional comments or notes. It is a good practice to preface any comments with the author (e.g. RP)
Note on G1: This is the estimate that was figured out at the beginning of the Sprint. For new tasks, this should be zero.
Note on H1: If the estimate needs to be revised, or it's a new task, the effort is here.
Note on I1: This is the increase\decrease in hours that needs to be tracked
Note on J1: Calculated field. It is the new estimate, if applicable.
Note on K1: The amount of hours that are still remaining for this task. Should be zero for a task that is completed, and should never be negative. If it drops below zero, it should be re-estimated.

## Lookups
Priority (1=Low, 9=High) | Status | Team
1 | 1 - Not Started | Ryan Bottriell
2 | 2 - In Progress | Zara Tooth
3 | 3 - Completed | Marco Brito
4 |  | Matthew Fournier
5
6
7
8
9
10
Note: To redefine a named value, go to Insert->Name->Define
Note on A1: Randar Puust: The priority. Items with a higher priority should be claimed first.
Note on B1: Randar Puust: Current status of this task. This can be used to ensure multiple people do not work on the same task. The filter can also be used to filter out any tasks that have already been completed.
Note on C1: Randar Puust: T4G: Who on the team has taken ownership of this work item.