## Sprint
Tasks | Product Backlog Item(s) | Description | Team | Status | Comments | Original Estimate (Hours) | New Estimate (Hours) | Change | Revised Value (Hours) | Amount Remaining (Hours) | Start | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday
scene 4 create asset for hand position | 10 |  | Marco Brito | 3 - Completed | rain | 1 |  |  |  |  | 0.5 | 1
scene 4 create new background, rain, and cloud to match scene design | 10 |  | Marco Brito | 3 - Completed | rain | 4 | [5 empty] | 1 |  | 2 | 1
Facebook Event | 36 |  | Marco Brito | 3 - Completed | Reactive Space | 0.5 | [10 empty] | 0.5
scene 2: draw lines debugging | 35 |  | Zara Tooth | 3 - Completed | [7 empty] | 2
scene 2: particle/hand connections are dynamic and boucy | 20 |  | Ryan Bottriell | 3 - Completed | lights | 1 | [5 empty] | 0.5
scene 4: rain rotates based on velocity | 18 |  | Ryan Bottriell | 3 - Completed |  | 0.5 | [5 empty] | 0.25
scene 4: rain color affected by particle velocity | 18 |  | Ryan Bottriell | 3 - Completed | rain | 2 |  |  | 2 | 2 |  | 0.5
debug kinect and opencv crash | 35 |  | Ryan Bottriell | 1 - Not Started |  | 2
scene 1 make scene resizeable | 35 |  | Ryan Bottriell | 2 - In Progress | [6 empty] | 0.25
scene 2 make scene resizeable | 35 |  | Zara Tooth | 1 - Not Started
scene 3 make scene resizeable | 35 |  |  | 1 - Not Started
scene 4 make scene resizeable | 35 |  |  | 1 - Not Started
scene 1: implement audio | 23 |  | Matthew Fournier | 3 - Completed |  | 0.5 | [5 empty] | 0.5
scene 4: implement audio | 26 |  | Matthew Fournier | 3 - Completed |  | 0.5 | [5 empty] | 0.5
Switching through the scenes | 35 |  | Zara Tooth | 3 - Completed |  | 0.5 | [10 empty] | 0.75
scene 3 fix explosion timing and drawing | 35 |  | Ryan Bottriell | 3 - Completed |  | 0.5 | [5 empty] | 0.5
fix particle contrusctors for scene swithing | 35 |  | Ryan Bottriell | 3 - Completed |  | 1 | 0.25 |  |  |  |  | 0.25
scene 2 fix connections when multiple hands | 35 |  | Ryan Bottriell | 3 - Completed | [12 empty] | 1
create image asset loader class | 33 |  | Zara Tooth | 3 - Completed |  | 2 | [10 empty] | 2
convert images to load with image loader | 33 |  | Zara Tooth | 2 - In Progress |  | 1 | [10 empty] | 0.5
General debugging | 35 |  | Matthew Fournier | 3 - Completed |  | 3 | 3 |  |  |  |  | 1.5 |  |  |  |  | 1.5
[5 empty] | Original | 11.5 |  | 0 | 2 | 2
[5 empty] | Revised | 2 |  |  |  | Daily Effort |  | 5.75 | 0 | 2 | 1 | 0 | 0.5 | 0
[5 empty] | Additional | -9.5 |  |  |  | Effort to Date |  | 9.25 | 0 | 2 | 3 | 3 | 3.5 | 3.5
[5 empty] | % Increase | -82.61% |  |  |  | Effort Left |  | -7.25 | 2 | 0 | -1 | -1 | -1.5 | -1.5
[10 empty] | % Remaining | 100% | -63.04% | 17.39% | 0% | -8.696% | -8.696% | -13.04% | -13.04%
[5 empty] | Remaining | 2
[5 empty] | % Remaining | 100%
[5 empty] | Team Size | 4
[5 empty] | Days Effort (est. @80%) | 0.078125
Note on A1: Short name. Should be unique.
Note on B1: This is a reference to the ID defined in the Product Backlog, if applicable.
Note on C1: Longer description of the work item. If it references any external documents, they should be listed here.
Note on D1: Who on the team has taken ownership of this work item.
Note on E1: Current status of this task. This can be used to ensure multiple people do not work on the same task. The filter can also be used to filter out any tasks that have already been completed.
Note on F1: Any additional comments or notes. It is a good practice to preface any comments with the author (e.g. RP)
Note on G1: This is the estimate that was figured out at the beginning of the Sprint. For new tasks, this should be zero.
Note on H1: If the estimate needs to be revised, or it's a new task, the effort is here.
Note on I1: This is the increase\decrease in hours that needs to be tracked
Note on J1: Calculated field. It is the new estimate, if applicable.
Note on K1: The amount of hours that are still remaining for this task. Should be zero for a task that is completed, and should never be negative. If it drops below zero, it should be re-estimated.

## Lookups
Priority (1=Low, 9=High) | Status | Team
1 | 1 - Not Started | Ryan Bottriell
2 | 2 - In Progress | Zara Tooth
3 | 3 - Completed | Marco Brito
4 |  | Matthew Fournier
5
6
7
8
9
10
Note: To redefine a named value, go to Insert->Name->Define
Note on A1: Randar Puust: The priority. Items with a higher priority should be claimed first.
Note on B1: Randar Puust: Current status of this task. This can be used to ensure multiple people do not work on the same task. The filter can also be used to filter out any tasks that have already been completed.
Note on C1: Randar Puust: T4G: Who on the team has taken ownership of this work item.