## Sprint
Tasks | Product Backlog Item(s) | Description | Team | Status | Comments | Original Estimate (Hours) | New Estimate (Hours) | Change | Revised Value (Hours) | Amount Remaining (Hours) | Start | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday
Background for scene 1 | 7 | finalize background assets for first scene to be loaded into project | Marco Brito | 3 - Completed | grid | 1 |  |  | 1 | 0 | [6 empty] | 1
Background for scene 2 | 8 | finalize background assets for second scene to be loaded into project | Marco Brito | 3 - Completed | lights | 1 |  |  | 1 | 0 | [6 empty] | 1
Background for scene 3 | 9 | finalize background assets for third scene to be loaded into project | Marco Brito | 3 - Completed | geo | 1 |  |  | 1 | 0 | [7 empty] | 1
Background for scene 4 | 10 | finalize background assets for fourth scene to be loaded into project | Marco Brito | 3 - Completed | rain | 1 |  |  | 1 | 0 | [7 empty] | 1
Particle assets scene 1 | 7 | finalize first scene particle assets to be loaded into project | Marco Brito | 3 - Completed | grid | 0.5 |  |  | 0.5 | 0 | [7 empty] | 0.5
Particle assets scene 2 | 8 | finalize second scene particle assets to be loaded into project | Marco Brito | 3 - Completed | lights | 0.5 |  |  | 0.5 | 0 | [7 empty] | 0.5
Particle assets scene 3 | 9 | finalize third scene particle assets to be loaded into project | Marco Brito | 3 - Completed | geo | 0.5 |  |  | 0.5 | 0 | [7 empty] | 0.5
Particle assets scene 4 | 10 | finalize fourth scene particle assets to be loaded into project | Marco Brito | 3 - Completed | rain | 0.5 |  |  | 0.5 | 0 | [7 empty] | 0.5
create audio scene 1 (background sounds) (Grid) | 11 | create initial background audio for first scene | Matthew Fournier | 3 - Completed |  | 1 |  |  | 1 | 0 |  |  | 1
create audio scene 2 (background sounds) (Lights) | 12 | create initial background audio for second scene | Matthew Fournier | 3 - Completed |  | 1 |  |  | 1 | 0 | [7 empty] | 1
create audio scene 3 (background sounds)(Geometric) | 13 | create initial background audio for third scene | Matthew Fournier | 3 - Completed |  | 1 |  |  | 1 | 1 |  | 1
create audio scene 4 background sounds)(Rain) | 14 | create initial background audio for fourth scene | Matthew Fournier | 3 - Completed |  | 1 |  |  | 1 | 1 |  | 1
create audio scene 1 (main interaction sounds) | 11 | create initial main interaction audio for first scene | Matthew Fournier | 3 - Completed | grid | 1 |  |  | 1 | 0 |  |  |  | 1
create audio scene 2 (main interaction sounds) | 12 | create initial main interaction audio for second scene | Matthew Fournier | 3 - Completed | lights | 2 |  |  | 2 | 0 |  |  | 1 | 1
create audio scene 3 (main interaction sounds) | 13 | create initial main interaction audio for third scene | Matthew Fournier | 3 - Completed | geo | 1 |  |  | 1 | 1 |  | 1
create audio scene 4 (main interaction sounds) | 14 | create initial main interaction audio for fourth scene | Matthew Fournier | 3 - Completed | rain | 1 |  |  | 1 | 0 |  |  |  | 1
integerate Kinect SDK to the project | 29 | initial integration for kinect SDK | Ryan Bottriell | 3 - Completed |  | 1 |  |  | 1 | 1 |  | 1
implement reading raw Kinect data | 29 | find and track hand movements using kinect | Ryan Bottriell | 3 - Completed |  | 2 |  |  | 2 | 2 |  | 2
scene 1: generate white particles for crowd | 15 |  | Ryan Bottriell | 3 - Completed | grid | 0.5 |  |  | 0.5 | 0.3 |  |  |  |  | 0.2
scene 1: create background grid particles and change to blue when white particles pass over | 15 |  | Ryan Bottriell | 3 - Completed | grid | 1 |  |  | 1 | 0.25 |  |  |  |  | 0.5 |  | 0.25
scene 1: implement background grid particles reacting to kinect movement(move) | 15 |  | Ryan Bottriell | 3 - Completed | grid | 1 | 2.5 | 1.5 | 2.5 | 1 | [6 empty] | 1.5
scene 1: implement background grid particles reacting to kinect movement(act like a flock of birds) | 15 |  | Ryan Bottriell | 3 - Completed | grid | 4 |  |  | 4 | 1 | [7 empty] | 3
scene 1: implement background grid particles reacting to kinect movement(change color to look angry) | 15 |  | Ryan Bottriell | 3 - Completed | grid | 1 |  |  | 1 | 0 |  |  |  |  | 0.5 |  | 0.5
scene 2: implement smoke assets | 16 |  | Zara Tooth | 1 - Not Started | lights | 1 |  |  | 1 | 1
scene 2: implement light object and shader | 16 |  | Zara Tooth | 2 - In Progress | lights | 5 |  |  | 5 | 2 | [6 empty] | 1.5 | 1.5
scene 2: generate particles crowd | 16 |  | Zara Tooth | 3 - Completed | lights | 2 |  |  | 2 | 0.5 | [6 empty] | 0.5 | 1
scene 2: particles connecting with active user hand locations | 16 |  | Zara Tooth | 1 - Not Started | lights | 5 |  |  | 5 | 5
scene 2: particles get dragged and thrown by active user | 16 |  | Zara Tooth | 1 - Not Started | lights | 5 |  |  | 5 | 5
scene 2: implement turning on/off lights when particles pass by | 16 |  | Zara Tooth | 3 - Completed | lights | 2 | 1.5 | -0.5 | 1.5 | 0 | [7 empty] | 1.5
scene 3: generate particles for crowd | 17 |  |  | 1 - Not Started | geo |  |  |  |  | 0
scene 3: implement assets for time dials where hands are | 17 |  |  | 1 - Not Started | geo |  |  |  |  | 0
scene 3: implement previous task only when dial is over a particles | 17 |  |  | 1 - Not Started | geo |  |  |  |  | 0
scene 3: implement explosion after dial is complete/ certain amount of time | 17 |  |  | 1 - Not Started | geo |  |  |  |  | 0
scene 4: implement rain particles being generated | 18 |  | Ryan Bottriell | 3 - Completed | rain | 0.5 |  |  | 0.5 | 0 | [7 empty] | 0.5
scene 4: implement rain particle changing color when kinect hand passes | 18 |  |  | 1 - Not Started | rain | 0.5 |  |  | 0.5 | 0.5
scene 4: implement mist over rain when hand passes over | 18 |  |  | 1 - Not Started | rain | 1.5 |  |  | 1.5 | 1.5
scene 4: implement rain reacting to hand gesture | 18 |  |  | 1 - Not Started | rain | 3 |  |  | 3 | 3
[5 empty] | Original | 51 |  | 1 | 52 | 27.05
[5 empty] | Revised | 52 |  |  |  | Daily Effort |  | 6 | 2 | 3 | 1.2 | 0 | 6.25 | 12.5
[5 empty] | Additional | 1 |  |  |  | Effort to Date |  | 30.95 | 2 | 5 | 6.2 | 6.2 | 12.45 | 24.95
[5 empty] | % Increase | 1.961% |  |  |  | Effort Left |  | 21.05 | 50 | 47 | 45.8 | 45.8 | 39.55 | 27.05
[10 empty] | % Remaining | 100% | 41.27% | 98.04% | 92.16% | 89.8% | 89.8% | 77.55% | 53.04%
[5 empty] | Remaining | 27.05
[5 empty] | % Remaining | 52.02%
[5 empty] | Team Size | 4
[5 empty] | Days Effort (est. @80%) | 1.0566
Note on A1: Short name. Should be unique.
Note on B1: This is a reference to the ID defined in the Product Backlog, if applicable.
Note on C1: Longer description of the work item. If it references any external documents, they should be listed here.
Note on D1: Who on the team has taken ownership of this work item.
Note on E1: Current status of this task. This can be used to ensure multiple people do not work on the same task. The filter can also be used to filter out any tasks that have already been completed.
Note on F1: Any additional comments or notes. It is a good practice to preface any comments with the author (e.g. RP)
Note on G1: This is the estimate that was figured out at the beginning of the Sprint. For new tasks, this should be zero.
Note on H1: If the estimate needs to be revised, or it's a new task, the effort is here.
Note on I1: This is the increase\decrease in hours that needs to be tracked
Note on J1: Calculated field. It is the new estimate, if applicable.
Note on K1: The amount of hours that are still remaining for this task. Should be zero for a task that is completed, and should never be negative. If it drops below zero, it should be re-estimated.

## Lookups
Priority (1=Low, 9=High) | Status | Team
1 | 1 - Not Started | Ryan Bottriell
2 | 2 - In Progress | Zara Tooth
3 | 3 - Completed | Marco Brito
4 |  | Matthew Fournier
5
6
7
8
9
10
Note: To redefine a named value, go to Insert->Name->Define
Note on A1: Randar Puust: The priority. Items with a higher priority should be claimed first.
Note on B1: Randar Puust: Current status of this task. This can be used to ensure multiple people do not work on the same task. The filter can also be used to filter out any tasks that have already been completed.
Note on C1: Randar Puust: T4G: Who on the team has taken ownership of this work item.