## Sprint
Tasks | Product Backlog Item(s) | Description | Team | Status | Comments | Original Estimate (Hours) | New Estimate (Hours) | Change | Revised Value (Hours) | Amount Remaining (Hours) | Start | Friday | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday
scene 2 assets optimized for implementation | 8 |  | Marco Brito | 3 - Completed | lights | 1 |  |  | 1 | 1
scene 3 assets optimized for implementation | 9 |  | Marco Brito | 2 - In Progress | geo, textured gradiant square | 1 |  |  | 1 | 1
scene 4 assets optimized for implementation | 10 |  | Marco Brito | 2 - In Progress | rain | 1 |  |  | 1 | 0.5 | [5 empty] | 0.5
scene 1: create static background | 7 |  | Marco Brito | 1 - Not Started | grid | 1
scene 1: implement static background | 15 |  | Ryan Bottriell | 1 - Not Started | grid | 0.25
scene 1: adjust colors to match scene design | 15 |  | Ryan Bottriell | 3 - Completed | grid | 0.25 | [5 empty] | 0.25
scene1: add perlin noise to grid particles | 15 |  | Ryan Bottriell | 3 - Completed | grid | 0.25 | [5 empty] | 0.25
scene 2: implement smoke assets with shader | 16 |  | Zara Tooth | 2 - In Progress | lights | 1 | 2 | 1 | 2 | 1 | [5 empty] | 1
scene 2: implement light object and shader | 16 |  | Zara Tooth | 2 - In Progress | lights | 5 | 7 | 2 | 7 | 5 | 3 |  |  |  |  | 2
scene 2: particles connecting with active user hand locations | 16 |  | Zara Tooth | 1 - Not Started | lights | 5 |  |  | 5 | 5
scene 2: implement hexparticles growing and changing color when connected to hands | 16 |  | Zara Tooth | 1 - Not Started | lights | 3
scene 2: create randomized turn on flicker effect for lights | 16 |  | Zara Tooth | 1 - Not Started | lights | 3
scene 2: particles get dragged and thrown by active user | 16 |  | Zara Tooth | 1 - Not Started | lights | 5 |  |  | 5 | 5
scene 3: generate particles for crowd | 17 |  | Matthew Fournier | 3 - Completed | geo | 3 |  |  | 3 | 3
scene 3: implement assets for time dials where hands are | 17 |  | Matthew Fournier | 1 - Not Started | geo | 1 |  |  | 1 | 1
scene 3: dials snap to particles and begin timing | 17 |  | Matthew Fournier | 3 - Completed | geo | 2 |  |  | 2 | 1.5 |  | 1 |  |  |  | 0.5
scene 3: dial times out and creates explosion effect on particle | 17 |  | Matthew Fournier | 2 - In Progress | geo | 4 |  |  | 4 | 3 |  | 1 |  |  |  | 1
scene 3: create particle effect for particle explosion |  |  | Matthew Fournier | 1 - Not Started | geo
scene 4: implement vector cloud to push rain particles | 18 |  | Marco Brito | 2 - In Progress | rain | 3 | [9 empty] | 1
scene 4: create rain particle shader to changing color when kinect hand passes | 18 |  | Marco Brito | 1 - Not Started | rain | 2 |  |  | 2 | 2
scene 4: hand gestures affect vector cloud | 18 |  | Marco Brito | 2 - In Progress | rain | 2 |  |  | 2 | 1 | [5 empty] | 1
alter people data structure to allow scenes to use different derived particle classes | 31 |  | Ryan Bottriell | 3 - Completed |  | 1 | [5 empty] | 2
smooth kinect interaction | 29 |  | Ryan Bottriell | 3 - Completed |  | 2 | [5 empty] | 1.5
kinect tracking hands, not replacing | 29 |  | Ryan Bottriell | 3 - Completed |  | 2.5 | [5 empty] | 1.5
get open cv reading data from webcam | 28 |  | Ryan Bottriell | 3 - Completed |  | 2 | [5 empty] | 3
open cv detecting points from webcam stream | 28 |  | Ryan Bottriell | 3 - Completed |  | 1 | [10 empty] | 1
[5 empty] | Original | 52.25 |  | 3 | 36 | 30
[5 empty] | Revised | 36 |  |  |  | Daily Effort |  | 10.5 | 0 | 0 | 0 | 7 | 1 | 0
[5 empty] | Additional | -16.25 |  |  |  | Effort to Date |  | 18.5 | 0 | 0 | 0 | 7 | 8 | 8
[5 empty] | % Increase | -31.1% |  |  |  | Effort Left |  | 17.5 | 36 | 36 | 36 | 29 | 28 | 28
[10 empty] | % Remaining | 100% | 33.49% | 68.9% | 68.9% | 68.9% | 55.5% | 53.59% | 53.59%
[5 empty] | Remaining | 30
[5 empty] | % Remaining | 83.33%
[5 empty] | Team Size | 4
[5 empty] | Days Effort (est. @80%) | 1.1719
Note on A1: Short name. Should be unique.
Note on B1: This is a reference to the ID defined in the Product Backlog, if applicable.
Note on C1: Longer description of the work item. If it references any external documents, they should be listed here.
Note on D1: Who on the team has taken ownership of this work item.
Note on E1: Current status of this task. This can be used to ensure multiple people do not work on the same task. The filter can also be used to filter out any tasks that have already been completed.
Note on F1: Any additional comments or notes. It is a good practice to preface any comments with the author (e.g. RP)
Note on G1: This is the estimate that was figured out at the beginning of the Sprint. For new tasks, this should be zero.
Note on H1: If the estimate needs to be revised, or it's a new task, the effort is here.
Note on I1: This is the increase\decrease in hours that needs to be tracked
Note on J1: Calculated field. It is the new estimate, if applicable.
Note on K1: The amount of hours that are still remaining for this task. Should be zero for a task that is completed, and should never be negative. If it drops below zero, it should be re-estimated.

## Lookups
Priority (1=Low, 9=High) | Status | Team
1 | 1 - Not Started | Ryan Bottriell
2 | 2 - In Progress | Zara Tooth
3 | 3 - Completed | Marco Brito
4 |  | Matthew Fournier
5
6
7
8
9
10
Note: To redefine a named value, go to Insert->Name->Define
Note on A1: Randar Puust: The priority. Items with a higher priority should be claimed first.
Note on B1: Randar Puust: Current status of this task. This can be used to ensure multiple people do not work on the same task. The filter can also be used to filter out any tasks that have already been completed.
Note on C1: Randar Puust: T4G: Who on the team has taken ownership of this work item.