## Sprint
Tasks | Product Backlog Item(s) | Description | Team | Status | Comments | Original Estimate (Hours) | New Estimate (Hours) | Change | Revised Value (Hours) | Amount Remaining (Hours) | Start | Saturday | Sunday | Monday | Tuesday | Wednesday | Thursday | Friday
Decide which SDE to use | 1 | Figure out the best SDE and version to use for development of our system | Marco Brito | 1 - Not Started |  | 0.5 |  |  | 0.5 | 0.5
Decide which SDK to use for Kinect | 1 | based on project needs, decide which Kinect library will work best | Marco Brito | 1 - Not Started |  | 0.5 |  |  | 0.5 | 0.5
Decide which SDK to use for computer vision | 1 | based on project needs, decide which computer vision library will work best | Marco Brito | 1 - Not Started |  | 0.5 |  |  | 0.5 | 0.5
Research what equipment is needed for running installation (PC specs) | 2 | Decide what kind of computer will be needed to run / render our final design | Matthew Fournier | 1 - Not Started |  | 0.5 |  |  | 0.5 | 0.5
Research what equipment is needed for setting up the installation (peripherals) | 2 | Decide what equipment will be needed to complete the installation (projector, screen etc) | Matthew Fournier | 1 - Not Started |  | 0.5 |  |  | 0.5 | 0.5
Mockup look for first scene | 3 | Create sketches/preliminary mock-ups for design | Ryan Bottriell | 3 - Completed |  | 2 | 2 | 0 | 2 | 2 | 2
Mockup interaction for first scene | 3 | figure out how user interaction affects the scene | Ryan Bottriell | 3 - Completed |  | 0.5 | 0.5 | 0 | 0.5 | 0.5 | 0.5
Mockup look for second scene | 4 | Create sketches/preliminary mock-ups for design | Zara Tooth | 3 - Completed |  | 2 | 2 | 0 | 2 | 2 | 2
Mockup interaction for second scene | 4 | figure out how user interaction affects the scene | Zara Tooth | 3 - Completed |  | 0.5 | 1 | 0.5 | 1 | 1 | 1
Mockup look for third scene | 5 | Create sketches/preliminary mock-ups for design | Marco Brito | 3 - Completed |  | 2 | 3 | 1 | 3 | 3 | 3
Mockup interaction for third scene | 5 | figure out how user interaction affects the scene | Marco Brito | 3 - Completed |  | 0.5 | 1 | 0.5 | 1 | 1 | 1
Mockup look for fourth | 6 | Create sketches/preliminary mock-ups for design | Matthew Fournier | 3 - Completed |  | 2 | 0.5 | -1.5 | 0.5 | 0.5 | 0.5
Mockup interaction for fourth scene | 6 | figure out how user interaction affects the scene | Matthew Fournier | 3 - Completed |  | 0.5 | 0.5 | 0 | 0.5 | 0.5 | 0.5
Create running OpenFrameworks project | 31 | Create running OpenFrameworks project in chosen SDE with chosen SDKs | Ryan Bottriell | 1 - Not Started |  | 3 |  |  | 3 | 3
Plan backend system code layout | 34 | create diagrams etc to describe effective code/class layout for project | Ryan Bottriell | 1 - Not Started |  | 1 |  |  | 1 | 1
Final design for first scene | 3 | take initial mockup and finalize it for implementation | Ryan Bottriell | 3 - Completed |  | 1 | 1 | 0 | 1 | 1 | 1
final interaction design for first scene | 3 | take initial mockup and finalize it for implementation | Ryan Bottriell | 3 - Completed |  | 1 | 1 | 0 | 1 | 1 | 1
Final design for second scene | 4 | take initial mockup and finalize it for implementation | Matthew Fournier | 3 - Completed |  | 1 | 1 | 0 | 1 | 1 | 1
final interaction design for second scene | 4 | take initial mockup and finalize it for implementation | Matthew Fournier | 3 - Completed |  | 1 | 1 | 0 | 1 | 1 | 1
Final design for third scene | 5 | take initial mockup and finalize it for implementation | Marco Brito | 3 - Completed |  | 1 | 1 | 0 | 1 | 1 | 1
final interaction design for third scenen | 5 | take initial mockup and finalize it for implementation | Marco Brito | 3 - Completed |  | 1 | 1 | 0 | 1 | 1 | 1
Final design for fourth scene | 6 | take initial mockup and finalize it for implementation | Zara Tooth | 1 - Not Started |  | 1 |  |  | 1 | 1
final interaction design for fourth scene | 6 | take initial mockup and finalize it for implementation | Zara Tooth | 1 - Not Started |  | 1 |  |  | 1 | 1
Designer approval of final scnene designs | 3 -> 6 | ensure final scene design fir with project and are at an acceptable level of goodness | Marco Brito | 2 - In Progress |  | 1 |  |  | 1 | 1 | 0.5
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[9 empty] | 0 | 0
[5 empty] | Original | 25.5 |  | 0.5 | 26 | 26
[5 empty] | Revised | 26 |  |  |  | Daily Effort |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Additional | 0.5 |  |  |  | Effort to Date |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | % Increase | 1.961% |  |  |  | Effort Left |  | 26 | 26 | 26 | 26 | 26 | 26 | 26
[10 empty] | % Remaining | 100% | 102% | 102% | 102% | 102% | 102% | 102% | 102%
[5 empty] | Remaining | 26
[5 empty] | % Remaining | 100%
[5 empty] | Team Size | 4
[5 empty] | Days Effort (est. @80%) | 1.0156
Note on A1: Short name. Should be unique.
Note on B1: This is a reference to the ID defined in the Product Backlog, if applicable.
Note on C1: Longer description of the work item. If it references any external documents, they should be listed here.
Note on D1: Who on the team has taken ownership of this work item.
Note on E1: Current status of this task. This can be used to ensure multiple people do not work on the same task. The filter can also be used to filter out any tasks that have already been completed.
Note on F1: Any additional comments or notes. It is a good practice to preface any comments with the author (e.g. RP)
Note on G1: This is the estimate that was figured out at the beginning of the Sprint. For new tasks, this should be zero.
Note on H1: If the estimate needs to be revised, or it's a new task, the effort is here.
Note on I1: This is the increase\decrease in hours that needs to be tracked
Note on J1: Calculated field. It is the new estimate, if applicable.
Note on K1: The amount of hours that are still remaining for this task. Should be zero for a task that is completed, and should never be negative. If it drops below zero, it should be re-estimated.

## Lookups
Priority (1=Low, 9=High) | Status | Team
1 | 1 - Not Started | Ryan Bottriell
2 | 2 - In Progress | Zara Tooth
3 | 3 - Completed | Marco Brito
4 |  | Matthew Fournier
5
6
7
8
9
10
Note: To redefine a named value, go to Insert->Name->Define
Note on A1: Randar Puust: The priority. Items with a higher priority should be claimed first.
Note on B1: Randar Puust: Current status of this task. This can be used to ensure multiple people do not work on the same task. The filter can also be used to filter out any tasks that have already been completed.
Note on C1: Randar Puust: T4G: Who on the team has taken ownership of this work item.