## Product Backlog
ID | Category | Feature | Priority 1=Low 9=High Stage | Effort Estimate (Hours) | Status | Comments | Unassigned Hours | In-Progress Hours | Completed Hours
1 | Research | Research best dev and software environment | 9 | 2 | 1 - Not Started |  | 2 | 0 | 0
2 | Research | Research best hardware environment | 9 | 2 | 1 - Not Started |  | 2 | 0 | 0
3 | Scene Concept Design | Design look, feel, sound for first unique scene | 9 | 2 | 1 - Not Started |  | 2 | 0 | 0
4 | Scene Concept Design | Design look, feel, sound for second unique scene | 9 | 2 | 1 - Not Started |  | 2 | 0 | 0
5 | Scene Concept Design | Design look, feel, sound for third unique scene | 9 | 2 | 1 - Not Started |  | 2 | 0 | 0
6 | Scene Concept Design | Design look, feel, sound for fourth unique scene | 9 | 2 | 1 - Not Started |  | 2 | 0 | 0
7 | Scene Asset Creation | Create all art for use in first scene development | 9 | 10 | 1 - Not Started |  | 10 | 0 | 0
8 | Scene Asset Creation | Create all art for use in second scene development | 9 | 10 | 1 - Not Started |  | 10 | 0 | 0
9 | Scene Asset Creation | Create all art for use in third scene development | 7 | 10 | 1 - Not Started |  | 10 | 0 | 0
10 | Scene Asset Creation | Create all art for use in fourth scene development | 6 | 10 | 1 - Not Started |  | 10 | 0 | 0
11 | Scene Asset Creation | Unique set of sounds for first scene | 8 | 6 | 1 - Not Started |  | 6 | 0 | 0
12 | Scene Asset Creation | Unique set of sounds for second scene | 8 | 8 | 1 - Not Started |  | 8 | 0 | 0
13 | Scene Asset Creation | Unique set of sounds for third scene | 8 | 6 | 1 - Not Started |  | 6 | 0 | 0
14 | Scene Asset Creation | Unique set of sounds for fourth scene | 8 | 6 | 1 - Not Started |  | 6 | 0 | 0
15 | Scene Development | Implement first scene concept in code (art only) | 9 | 8 | 1 - Not Started |  | 8 | 0 | 0
16 | Scene Development | Implement second scene concept in code (art only) | 9 | 8 | 1 - Not Started |  | 8 | 0 | 0
17 | Scene Development | Implement third scene concept in code (art only) | 7 | 8 | 1 - Not Started |  | 8 | 0 | 0
18 | Scene Development | Implement fourth scene concept in code (art only) | 6 | 8 | 1 - Not Started |  | 8 | 0 | 0
19 | Scene Development | Implement user interaction into first scene | 9 | 4 | 1 - Not Started |  | 4 | 0 | 0
20 | Scene Development | Implement user interaction into second scene | 9 | 4 | 1 - Not Started |  | 4 | 0 | 0
21 | Scene Development | Implement user interaction into third scene | 8 | 4 | 1 - Not Started |  | 4 | 0 | 0
22 | Scene Development | Implement user interaction into fourth scene | 7 | 4 | 1 - Not Started |  | 4 | 0 | 0
23 | Scene Development | Implement sounds for first scene | 8 | 2 | 1 - Not Started |  | 2 | 0 | 0
24 | Scene Development | Implement sounds for second scene | 8 | 2 | 1 - Not Started |  | 2 | 0 | 0
25 | Scene Development | Implement sounds for third scene | 7 | 2 | 1 - Not Started |  | 2 | 0 | 0
26 | Scene Development | Implement sounds for fourth scene | 6 | 2 | 1 - Not Started | requires task 1 first | 2 | 0 | 0
27 | Computer Vision Development | System detects users as they enter the space | 9 | 15 | 1 - Not Started |  | 15 | 0 | 0
28 | Computer Vision Development | System tracks users moving through the space | 9 | 15 | 1 - Not Started |  | 15 | 0 | 0
29 | Kinect Development | Kinect recognizes active users and their hand movements | 9 | 10 | 1 - Not Started | Kinect SDK will be used | 10 | 0 | 0
30 | Runtime Development | System tracks active users hand movements and provides it to the scenes | 9 | 4 | 1 - Not Started |  | 4 | 0 | 0
31 | Runtime Development | System which manages scenes and backend data | 9 | 3 | 1 - Not Started | includes managing / passing input data and switching between scenes | 3 | 0 | 0
32 | Runtime Development | System can load and play sounds for each scene | 8 | 5 | 1 - Not Started
33 | Runtime Development | System can load and manage art assets for the scenes | 9 | 5 | 1 - Not Started
34 | Runtime Design | Plan backend system | 9 | 3 | 1 - Not Started
Next ID: 35 |  |  | Totals (Hours) | 194
|  |  | per person (aprox) | 48.5
|  |  | per week (aprox) | 27.7143
|  |  | per person per week (aprox) | 6.9286
Note on B1: High level classification of the task
Note on C1: A 3 or more sentence description of the requirement.
Note on F1: Current status of this task. This can be used to ensure multiple people do not work on the same task. The filter can also be used to filter out any tasks that have already been completed.
Note on G1: Any additional comments or notes. It is a good practice to preface any comments with the author (e.g. RP)
Note on A38: Randar Puust: This is the next available ID to use.

## Report Data
Effort Status
Total Work | Not Started | In-Progress | Completed
194 | 181 | 0 | 0

## Lookups
Priority | Business Value | Status | Categories
1 | Low | 1 - Not Started | Kinect Development
2 | Med | 2 - In Progress | Computer Vision Development
3 | High | 3 - Completed | Scene Development
4 |  |  | Scene Asset Creation
5 |  |  | Scene Concept Design
6 |  |  | Runtime Development
7 |  |  | User Input
Runtime Design
8 |  |  | Research
9
10